## Sheet1
velocity
[5 empty] | sprint | completed | commitment
[5 empty] | sprint 1 | 15 | 18
[5 empty] | sprint 2 | 20 | 21
[5 empty] | sprint 3 | 10 | 11
[5 empty] | sprint 4 | 10 | 10
the velocity =(15+20+10+10)/4= 13
burndown cahrt
sprint 2
| task | start hours | 1st (2days) | 2nd (2 days) | 3rd (2days) | 4th(2days) | 5th(2days) | 6th(2days) | 7 th(2days)
| desgin interface |  | 20 | 20 | 20 | 0 | 0 | 0 | 0
| database |  | 20 | 10 | 20 | 0 | 0 | 0 | 0
| design interface |  | 20 | 20 | 10 | 0 | 0 | 0 | 0
| database |  | 0 | 0 | 0 | 20 | 10 | 10 | 0
| design interface |  | 0 | 0 | 0 | 10 | 20 | 20
| database |  | 0 | 0 | 0 | 20 | 15 | 15 | 0
| actual remaining effort | 1464 | 1404 | 1354 | 1304 | 1254 | 1209 | 1164 | 1164
| estimated remaning effort | 1464 | 1412 | 1360 | 1308 | 1256 | 1204 | 1152 | 1100
sprint 3
| task | start hours | 1st (2days) | 2nd (2 days) | 3rd (2days) | 4th(2days) | 5th(2days) | 6th(2days) | 7 th(2days)
| desgin interface |  | 10 | 20 | 10 | 0 | 0 | 0 | 0
| database |  | 20 | 10 | 20 | 0 | 0 | 0 | 0
| design interface |  | 0 | 0 | 0 | 20 | 20 | 20 | 0
| database |  | 0 | 0 | 0 | 20 | 15 | 20 | 0
| actual remaining effort | 1164 | 1143 | 1104 | 1074 | 1034 | 1004 | 964 | 964
| estimated remaning effort | 1464 | 1412 | 1360 | 1308 | 1256 | 1204 | 1152 | 1100
sprint 4
|  | task | start hours | 1st (2days) | 2nd (2 days) | 3rd (2days) | 4th(2days) | 5th(2days) | 6th(2days) | 7 th(2days)
|  | desgin interface |  | 20 | 20 | 20 | 0 | 0 | 0 | 0
|  | design interface |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | design interface |  | 20 | 20 | 20 | 0 | 0 | 0 | 0
|  | actual remaining effort | 964 | 924 | 884 | 844 | 844 | 844 | 844 | 844
|  | estimated remaning effort | 1464 | 1412 | 1360 | 1308 | 1256 | 1204 | 1152 | 1100
release chart
there is 6 developer in the team each one work 50 hour per week so the 300 hour per week for 2 weeks 600 for the whole release 2400 hour
|  | sprint | hours
|  | sprint 1 | 0 | sprint 4 | 120
|  | sprint 2 | 300 | sprint 3 | 205
|  | to do | 1464 | 1098 | 732 | 366
|  | done | 0 | 300 | 205 | 120